## Project Status
MATERIAL KING - Project Status Report
Generated: 21 Mar 2026 ¦ Team: 6-7 devs ¦ Start: 22 Jan 2026 ¦ Deadline: 30 Apr 2026 ¦ 5.7 weeks remaining
Module / Feature | Area | Status | Notes
BACKEND - COMPLETED (Jan 22 - Mar 10, ~7 weeks)
Auth Module (register, login, JWT, refresh, logout) | Backend | DONE | Full JWT auth with role middleware, account locking after 5 failed attempts
Products CRUD API | Backend | DONE | List, create, update, delete + active endpoint with filters
Brands CRUD API | Backend | DONE | List, create, update, delete
Categories CRUD API | Backend | DONE | List, create, update, delete + parent/child hierarchy + reorganize endpoint
Vendors CRUD API | Backend | DONE | List, create, update, delete
Zones CRUD API (with pincodes) | Backend | DONE | Zone-vendor assignments, pincode mapping
Buyers CRUD API (with projects) | Backend | DONE | Buyer + project management
Dealers CRUD API | Backend | DONE | With credit limit, approval status
Orders CRUD API (with items) | Backend | DONE | Order creation with transaction, line items, cart auto-clear
Cart API (server-side + guest sync) | Backend | DONE | Add/update/remove/clear + sync on login
Wishlist API | Backend | DONE | Add/remove/list user wishlist
Coupon API | Backend | DONE | Validate/apply coupons, percentage/fixed, usage limits
Address API | Backend | DONE | CRUD for user addresses with default address support
DB Schema (15+ tables) + Seed Script | Backend | DONE | Full schema with migration patches
Validation & Error Middleware | Backend | DONE | Request validation middleware
Role-based Access Control | Backend | DONE | Admin, dealer, buyer, vendor roles
FRONTEND - FOUNDATION (COMPLETED)
Vite + React 19 + TypeScript | Frontend | DONE | Project scaffolded and running
Tailwind CSS Config (custom MK theme) | Frontend | DONE | mk-red, mk-gray palette, Montserrat font
BrowserRouter + Route Definitions | Frontend | DONE | Full route tree: public, admin, account sections
React Query (QueryClientProvider) | Frontend | DONE | Configured with retry:1, staleTime:30s
Axios API Client + Token Refresh | Frontend | DONE | Auto-refresh on 401, concurrent request queue
AuthContext + useAuth hook | Frontend | DONE | Login/logout/updateUser/isAdmin, auto-load on mount
Protected Routes / Route Guards | Frontend | DONE | ProtectedRoute component with loading spinner
API Service Layer (13 modules) | Frontend | DONE | product, category, brand, vendor, zone, dealer, buyer, order, auth, cart, coupon, wishlist, address
Login Page | Frontend | DONE | Email/password login with validation
Register Page | Frontend | DONE | User registration with role selection
FRONTEND - ADMIN CRUD MODULES (COMPLETED)
Admin Dashboard | Frontend | DONE | Stats cards (orders, revenue, products, buyers, dealers) + recent orders table
Products Module (list + forms) | Frontend | DONE | Full CRUD with 4-tab form (basic, dimensions, attributes, packaging)
Brands Module (list + forms) | Frontend | DONE | CRUD with DataTable + FormModal
Categories Module (list + forms) | Frontend | DONE | CRUD with parent/child hierarchy
Vendors Module (list + forms) | Frontend | DONE | CRUD with DataTable + FormModal
Zones Module (list + forms) | Frontend | DONE | CRUD with DataTable + FormModal
Buyers Module (list + forms) | Frontend | DONE | CRUD with DataTable + FormModal
Dealers Module (list + forms) | Frontend | DONE | CRUD with DataTable + FormModal
Orders Module (list + detail) | Frontend | DONE | Admin order management with status updates
Reusable UI Components | Frontend | DONE | DataTable, FormField, FormModal, StatusBadge
FRONTEND - STOREFRONT PAGES (COMPLETED)
Public Header + Nav with Category Hover Dropdowns | Frontend | DONE | 7 merged categories, hover subcategory menus, linked to products
Public Footer | Frontend | DONE | Footer with links
Home Page | Frontend | DONE | Hero section + featured products
Products List Page | Frontend | DONE | Filters (category, brand, price range, search, sort)
Product Detail Page | Frontend | DONE | Product info tabs, wishlist, add to cart
Categories Page | Frontend | DONE | Category grid with subcategory tags
Cart Page | Frontend | DONE | Cart items, coupon apply, tax/shipping calc
Checkout Page | Frontend | DONE | Address selection, payment method, order placement
Order Confirmation Page | Frontend | DONE | Post-checkout confirmation (protected)
About Page | Frontend | DONE | Static about us page
Contact Page | Frontend | DONE | Contact form
FRONTEND - BUYER ACCOUNT (COMPLETED)
My Account Page | Frontend | DONE | Profile management
My Orders Page | Frontend | DONE | Order history with detail view
Addresses Page | Frontend | DONE | Saved addresses CRUD with default
Wishlist Page | Frontend | DONE | Wishlist management
BACKEND - PHASE 1 COMPLETED (Mar 21)
Search & Filtering + Pagination (server-side) | Backend | DONE | Full pagination across ALL endpoints (products, orders, brands, categories, vendors, zones, buyers, dealers, coupons, wishlist, addresses, cart)
Order Workflow State Machine | Backend | DONE | Full state machine: pending→confirmed→processing→shipped→delivered, transition validation, stock restore on cancel
Inventory Management (stock decrement + alerts) | Backend | DONE | Auto-decrement on order, FOR UPDATE locking, restore on cancel, low-stock alerts API, inventory summary endpoint
File Upload Middleware (Multer/S3) | Backend | DONE | Multer disk storage, single/multiple upload, file type validation, 10MB limit, /api/upload endpoints
BACKEND - PENDING (must complete by Apr 30)
Payment Integration (Razorpay) | Backend | MISSING | No payment gateway code. Only COD supported
Invoice Generation (PDF) | Backend | MISSING | No PDF generation library or templates
Pricing Tiers / Discount Structures | Backend | PARTIAL | Dealer credit + coupon system exists; tier-based pricing logic not implemented
Delivery Tracking | Backend | PARTIAL | Basic date fields; no tracking numbers or logistics API
Reporting / Analytics APIs | Backend | MISSING | No sales reports, trend analytics, export APIs
Notifications (Email/SMS) | Backend | MISSING | No nodemailer/twilio integration
FRONTEND - PENDING (must complete by Apr 30)
Inventory Module UI | Frontend | MISSING | Stock levels, alerts, reorder points dashboard
Payment Module UI | Frontend | MISSING | Payment processing screens (Razorpay integration)
Invoice Module UI | Frontend | MISSING | View/download invoices as PDF
Delivery Tracking UI | Frontend | MISSING | Track order delivery status with timeline
Reporting / Dashboard Charts | Frontend | MISSING | Sales summary, top products, dealer analytics with charts
Role-based Dashboards (dealer, buyer, vendor) | Frontend | MISSING | Different dashboards per role
Products File Upload UI | Frontend | MISSING | Image upload in product forms (needs Multer backend)
Responsive Design / Mobile | Frontend | PARTIAL | Desktop works; mobile nav exists but needs polish
Admin Dashboard Charts | Frontend | PARTIAL | Stats cards done; no charts/graphs, no date-range analytics

## Gantt Chart
MATERIAL KING - Gantt Chart (Jan 22, 2026 - Apr 30, 2026)
Team: 6-7 Developers ¦ Total: 14 Weeks ¦ Elapsed: 8 weeks ¦ REMAINING: 5.7 weeks ¦ Deadline: 30 Apr 2026
Task | Area | Team | Start Date | End Date | Wks | W1 19 Jan | W2 26 Jan | W3 02 Feb | W4 09 Feb | W5 16 Feb | W6 23 Feb | W7 02 Mar | W8 09 Mar | W9 16 Mar | W10 23 Mar | W11 30 Mar | W12 06 Apr | W13 13 Apr | W14 20 Apr | W15 27 Apr
COMPLETED: Backend CRUD & Setup (Jan 22 - Mar 10)
Project Setup (Vite, Express, DB, TypeScript) | Full Stack | All Devs | 2026-01-19 | 2026-02-01 | 2 | ✓ | ✓
Auth Module (JWT, register, login, roles) | Backend | Dev 3, Dev 4 | 2026-01-26 | 2026-02-08 | 2 |  | ✓ | ✓
Products + Brands + Categories CRUD APIs | Backend | Dev 1, Dev 2 | 2026-02-02 | 2026-02-15 | 2 |  |  | ✓ | ✓
Vendors + Zones CRUD APIs | Backend | Dev 3, Dev 5 | 2026-02-09 | 2026-02-22 | 2 |  |  |  | ✓ | ✓
Buyers + Dealers + Orders CRUD APIs | Backend | Dev 4, Dev 6, Dev 7 | 2026-02-16 | 2026-03-08 | 3 |  |  |  |  | ✓ | ✓ | ✓
Cart + Wishlist + Coupon + Address APIs | Backend | Dev 3, Dev 7 | 2026-02-23 | 2026-03-08 | 2 | [5 empty] | ✓ | ✓
DB Schema (15+ tables) + Seed + Middleware | Backend | Dev 3 | 2026-02-23 | 2026-03-08 | 2 | [5 empty] | ✓ | ✓
Frontend Scaffolding (Axios, AuthContext, Header) | Frontend | Dev 1 | 2026-02-23 | 2026-03-08 | 2 | [5 empty] | ✓ | ✓
PHASE 1: FOUNDATION (Mar 10-23) ✅ COMPLETED
Fix Tailwind + BrowserRouter + React Query setup | Frontend | Dev 1 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Auth Pages (Login + Register + Token Refresh) | Frontend | Dev 2 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Protected Routes + useAuth hook | Frontend | Dev 1 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
API Service Layer (13 modules) | Frontend | Dev 1, Dev 2 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Search & Filtering (product backend) | Backend | Dev 3 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Storefront: Home, Products, Detail, Cart, Checkout | Frontend | Dev 1, Dev 2, Dev 5 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Buyer Account: Orders, Addresses, Wishlist | Frontend | Dev 2, Dev 6 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Category Reorganization + Nav Hover Dropdowns | Frontend | Dev 1 | 2026-03-16 | 2026-03-22 | 1 | [8 empty] | ✓
PHASE 1 REMAINING (Mar 16-23) ✅ COMPLETED
Server-side Pagination (all endpoints) | Backend | Dev 3 | 2026-03-16 | 2026-03-22 | 1 | [8 empty] | ✓
File Upload Middleware (Multer/S3) | Backend | Dev 4 | 2026-03-16 | 2026-03-22 | 1 | [8 empty] | ✓
Order Workflow State Machine | Backend | Dev 7 | 2026-03-16 | 2026-03-22 | 1 | [8 empty] | ✓
Inventory Decrement on Order + Alerts | Backend | Dev 4 | 2026-03-16 | 2026-03-22 | 1 | [8 empty] | ✓
PHASE 2: CORE MODULES (Mar 24 - Apr 6)
Products Module UI (list + forms + 4 tabs) | Frontend | Dev 1 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Brands + Categories Module UI | Frontend | Dev 2 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Vendors Module UI | Frontend | Dev 5 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Zones Module UI | Frontend | Dev 5 | 2026-03-09 | 2026-03-15 | 1 | [7 empty] | ✓
Dealers Module UI | Frontend | Dev 6 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Buyers Module UI | Frontend | Dev 2 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Orders Module UI (admin) | Frontend | Dev 1, Dev 2 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Admin Dashboard (stats + recent orders) | Frontend | Dev 2, Dev 5 | 2026-03-09 | 2026-03-22 | 2 | [7 empty] | ✓ | ✓
Products File Upload UI (needs Multer) | Frontend | Dev 1 | 2026-03-23 | 2026-03-29 | 1
Pricing Tiers / Discount Backend | Backend | Dev 4 | 2026-03-23 | 2026-03-29 | 1
Payment Integration Backend (Razorpay) | Backend | Dev 7 | 2026-03-23 | 2026-04-05 | 2
Invoice Generation Backend (PDF) | Backend | Dev 3 | 2026-03-30 | 2026-04-05 | 1
PHASE 3: BUSINESS LOGIC & DASHBOARD (Apr 7 - Apr 20)
Inventory Module UI (stock levels, alerts) | Frontend | Dev 5 | 2026-04-06 | 2026-04-12 | 1
Payment Module UI (Razorpay frontend) | Frontend | Dev 6 | 2026-04-06 | 2026-04-12 | 1
Invoice Module UI (view/download PDF) | Frontend | Dev 6 | 2026-04-13 | 2026-04-19 | 1
Admin Dashboard Charts (recharts/chart.js) | Frontend | Dev 2, Dev 5 | 2026-04-06 | 2026-04-19 | 2
Reporting APIs (sales, top products, analytics) | Backend | Dev 3 | 2026-04-06 | 2026-04-12 | 1
Delivery Tracking Backend + UI | Full Stack | Dev 7 | 2026-04-06 | 2026-04-19 | 2
Notifications Backend (Email/SMS) | Backend | Dev 4 | 2026-04-13 | 2026-04-19 | 1
PHASE 4: POLISH & LAUNCH (Apr 21 - Apr 30) 🚀 DEADLINE
Role-based Dashboards (dealer, buyer, vendor) | Frontend | Dev 1, Dev 6 | 2026-04-20 | 2026-04-26 | 1
Reporting Dashboard Charts (frontend) | Frontend | Dev 2, Dev 5 | 2026-04-20 | 2026-04-26 | 1
Responsive Design + Mobile Polish | Frontend | Dev 3 | 2026-04-20 | 2026-04-26 | 1
Integration Testing (API + UI) | Full Stack | All Devs | 2026-04-20 | 2026-04-26 | 1
Bug Fixes & Performance Optimization | Full Stack | All Devs | 2026-04-27 | 2026-05-03 | 1
UAT + Production Deployment | Full Stack | All Devs | 2026-04-27 | 2026-05-03 | 1
▲ TODAY (Mar 21, 2026) — 5.7 weeks to deadline | [13 empty] | ▲ NOW
LEGEND:
Completed (Jan 22 - Mar 10)
Phase 1: Foundation (Mar 10-23) — COMPLETED
Phase 2: Core CRUD (Mar 24 - Apr 6) — frontend DONE, backend partial
Phase 3: Business Logic & Dashboard (Apr 7-20)
Phase 4: Polish & Launch (Apr 21-30)
TODAY marker (Mar 21)

## Summary
PROJECT SUMMARY
Start: 22 Jan 2026 ¦ Today: 21 Mar 2026 ¦ Deadline: 30 Apr 2026
TIMELINE
Project Start | 22 Jan 2026
Today | 21 Mar 2026 | 8 weeks elapsed
Hard Deadline | 30 Apr 2026 | 5.7 weeks remaining
Total Duration | 14 weeks | No buffer for delays
COMPLETION STATUS | Count | Details
Backend CRUD Completed | 17 modules | Auth, Products, Brands, Categories, Vendors, Zones, Buyers, Dealers, Orders, Cart, Wishlist, Coupon, Address, Schema, Seed, Validation, RBAC
Backend Features Completed (Phase 1) | 4 features | Pagination (all endpoints), File Upload (Multer), Order State Machine, Inventory Decrement + Alerts
Backend Features Pending | 4 features | Payments (Razorpay), Invoices (PDF), Reporting APIs, Notifications (Email/SMS)
Backend Features Partial | 2 features | Pricing Tiers (coupon done, tier logic pending), Delivery Tracking (basic fields, no logistics API)
Frontend Completed | 48 items | All admin CRUD (9 modules), all storefront pages (11), buyer account (4), foundation (10), UI components (4), nav/footer
Frontend Pending | 8 items | Inventory UI, Payment UI, Invoice UI, Delivery UI, Dashboard Charts, Role-based Dashboards, File Upload UI, Responsive polish
Overall Completion | ~68% | Backend CRUD + Phase 1 features + Frontend CRUD + Storefront all done. Remaining: business logic backends + specialized UIs.
RISK ASSESSMENT
Schedule Risk | MEDIUM-LOW | Phase 1 complete. ~32% work in 5.7 weeks. On track with focused sprints.
Critical Path | Payments + Invoices | These depend on each other — next priority in Phase 2
Parallel Tracks Needed | YES | Backend features (payments, invoices) + Frontend UIs simultaneously
Recommended Action | FOCUSED SPRINTS | Start Phase 2: Razorpay + Invoice PDF + Pricing Tiers next week
PHASE PLAN (REMAINING) | Duration | Focus
Phase 1 | Mar 16-23 (1 wk) | COMPLETED: Pagination, File Upload, Order State Machine, Inventory Decrement
Phase 2 Remaining | Mar 24 - Apr 6 (2 wks) | Pricing tiers, Razorpay payment backend, Invoice PDF generation, Product file upload UI
Phase 3: Business Logic | Apr 7-20 (2 wks) | Inventory UI, Payment UI, Invoice UI, Dashboard charts, Reporting APIs, Delivery tracking, Notifications
Phase 4: Polish & Launch | Apr 21-30 (1.5 wks) | Role-based dashboards, responsive design, testing, UAT, deployment
WHAT WAS DONE AHEAD OF SCHEDULE
All Admin CRUD UIs (9 modules) | Phase 2 → Done in Phase 1 | Products, Brands, Categories, Vendors, Zones, Buyers, Dealers, Orders, Dashboard
All Storefront Pages (11 pages) | Phase 2-3 → Done in Phase 1 | Home, Products, Detail, Cart, Checkout, Confirmation, Categories, About, Contact + Header/Footer
Buyer Account (4 pages) | Phase 3 → Done in Phase 1 | My Account, My Orders, Addresses, Wishlist
Cart + Wishlist + Coupon APIs | Not in plan → Done | Server-side cart, wishlist, coupon validation — bonus features
TEAM ALLOCATION (suggested for remaining)
Dev 1 (Frontend Lead) |  | File Upload UI → Role-based Dashboards → Responsive polish
Dev 2 (Frontend) |  | Dashboard Charts → Reporting UI → Integration testing
Dev 3 (Backend + Frontend) |  | Pagination → Invoice PDF backend → Reporting APIs
Dev 4 (Backend Lead) |  | File Upload Multer → Inventory decrement → Notifications
Dev 5 (Frontend) |  | Inventory UI → Dashboard charts → Responsive design
Dev 6 (Frontend) |  | Payment UI → Invoice UI → Role-based views
Dev 7 (Backend) |  | Order State Machine → Razorpay → Delivery tracking